## Progress
Thing | Value | Done
Plan
Scope | 5 | Yes | 5 | 0
Schedule | 2 | Sure | 2 | 0
UX | 10 | ?? | 6 | 4
Risk Mgmt | 3 | ?? | 0 | 3
Requirements
Use Case Diagram | 5 | ALL DONE, EVERYTHING | 5 | 0
Text Use Cases | 10 | ALL DONE, EVERYTHING | 10 | 0
Test Cases | 10 | Few | 3 | 7
Class Diagram | 10 | DB Half likely sufficient, having vue components as classes sloppy | 9 | 1
Sequence Diagrams | 10 | Few | 4 | 6
Architecture | 5 | Yes, with hopefully better symbolism | 5 | 0
Detailed design (attr, meth) | 5 | There for what matters | 5 | 0
Test Cases | 5 | Nope | 0 | 5
Prototype Demo | 20 | TEST MORE | 17 | 3
| 100 |  | 71

## SFD completion
Section | Name | Completion | Notes
1.1 | System purpose | OK
1.2 | System scope | OK
1.3 | Dev Methodo | OK but not followed
1.4 | Defn, Acro, Abbr | Maybe More
1.5 | Doc Overview | OK boilerplate
2 | Current System
3.1 | Proj Organiz
3.2 | Soft/Hardware Reqs
3.3 | Work Breakdown | ???
4.1 | Func/Non reqs
4.2 | Personas
4.3 | Use Case Diagrams
5.1 | Arch overview
5.2 | Subsystem Decomp
5.3 | Persistent Data Mgmt
6.1 | Object Overview
6.2 | Object Interaction
6.3 | Detailed Class Design |  | Get new file
7 | Testing |  | Eric
8 | Glossary |  | TODO
9.1 | Gantt Chart |  | Scrap
9.2 | Use Cases | Just put it together | Doco repo
9.3 | User Interface |  | Copy new Screenshots
9.4 | ??? |  | Missing, ignore?
9.5 | Class Interfaces |  | Create These

## Use Cases
Category | Title | Status
Layout | Add Node To Tree | Done
| Remove Node From Tree | Done
| Reparent Node | Done
| Reorder Node | Done
| Edit Node Info | Done
| Save Layout | Done
| Create Layout | Done
| Delete Layout | Done
User | Create User | Done
| Remove User | Done
| Edit User Roles | Done
| Update Password | Done
| Authenticate | Done
| Logout | Done
Media | Upload Media Item | Done
| Update Media Properties | Done
| Create Media Folder | Done
| Move Item To Folder | Done
| Delete Media Folder | Done
| Delete Media Item | Done
Player | Create Player | Done
| Edit Player Info | Done
| Set Player Layouts | Done
| Deploy Player | Done
| Delete Player | Done
| Get Player Statuses | Done